## Project Plan
Project: | EventsPlanner | [9 empty] | Project Timeline
Project Memebers:
| Ted Ian Osias |  | Priority
| Charlie Ahl Arreglo |  |  | High
| Aislinn Jewel Caparoso |  |  | Medium
| James Suson |  |  | Low
Noville Lao Villanueva
Louie Romares
Tasks |  |  |  | Assigned Member | Timeline |  |  |  | Priority | Status
[5 empty] | PLANNED |  | ACTUAL
[5 empty] | START | END | START | END | time axis 2015-07-03 to 2015-09-30
Back-end(1.0)
1.1 Create Entity Class
| 1.1.1 | TODO |  | Ted Ian Osias |  |  |  | NA | High | NOT DONE | 2015-07-20: 1.1.1; 2015-07-28: Unit Test
| 1.1.2 | Event |  | Charlie Ahl Arreglo |  |  |  | NA | High | NOT DONE | 2015-07-20: 1.1.2; 2015-07-28: Unit Test
| 1.1.3 | User |  | Aislinn Jewel Caparoso |  |  |  | NA | Medium | NOT DONE
| 1.1.4 | UserInfo |  | James Suson |  |  |  | NA | Medium | NOT DONE
1.2 Create DataAccesObjects
| 1.2.1 | UserDAO
|  | 1.2.1.1 | Create | Aislinn Jewel Caparoso |  |  |  | NA | Medium | NOT DONE | 2015-07-30: 1.2.1.1; 2015-08-05: Unit Test
|  | 1.2.1.2 | Update | Louie Romares |  |  |  | NA | Medium | NOT DONE | 2015-08-07: 1.2.1.2; 2015-08-12: Unit Test
|  | 1.2.1.3 | Delete | James Suson |  |  |  | NA | Medium | NOT DONE | 2015-08-07: 1.2.1.3; 2015-08-12: Unit Test
|  | 1.2.1.4 | Read | Charlie Ahl Arreglo |  |  |  | NA | Medium | NOT DONE | 2015-08-07: 1.2.1.4; 2015-08-12: Unit Test
| 1.2.2 | UserInfoDAO
|  | 1.2.2.1 | Create | Noville Lao Villanueva |  |  |  | NA | Low | NOT DONE | 2015-08-07: 1.2.2.1; 2015-08-12: Unit Test
|  | 1.2.2.2 | Update | Ted Ian Osias |  |  |  | NA | Low | NOT DONE | 2015-08-14: 1,2.2.2; 2015-08-20: Unit Test
|  | 1.2.2.3 | Delete | Aislinn Jewel Caparoso |  |  |  | NA | Low | NOT DONE | 2015-08-14: 1.2.2.3; 2015-08-20: Unit Test
|  | 1.2.2.4 | Read | Louie Romares |  |  |  | NA | Low | NOT DONE | 2015-08-24: 1.2.2.4; 2015-08-27: Unit Test
| 1.2.3 | EventDAO
|  | 1.2.3.1 | Create | Noville Lao Villanueva |  |  |  | NA | High | NOT DONE | 2015-07-20: 1.2.3.1; 2015-07-28: Unit Test
|  | 1.2.3.2 | Update | Louie Romares |  |  |  | NA | High | NOT DONE | 2015-07-20: 1.2.3.2; 2015-07-28: Unit Test
|  | 1.2.3.3 | Delete | Aislinn Jewel Caparoso |  |  |  | NA | High | NOT DONE | 2015-07-20: 1.2.3.3; 2015-07-28: Unit Test
|  | 1.2.3.4 | Read | James Suson |  |  |  | NA | High | NOT DONE | 2015-07-20: 1.2.3.4; 2015-07-28: Unit Test
1.3 Create Controllers
| 1.3.1 | Login-Controller
|  | 1.3.1.1 | Authenticate | Ted Ian Osias |  |  |  | NA | Medium | NOT DONE | 2015-08-07: 1.3.1.1; 2015-08-12: Unit Test
|  | 1.3.1.2 | Add | Louie Romares |  |  |  | NA | Medium | NOT DONE | 2015-08-14: 1.3.1.2; 2015-08-20: Unit Test
|  | 1.3.1.3 | Delete | James Suson |  |  |  | NA | Medium | NOT DONE | 2015-08-14: 1.3.1.3; 2015-08-20: Unit Test
|  | 1.3.1.4 | Update | Charlie Ahl Arreglo |  |  |  | NA | Medium | NOT DONE | 2015-08-14: 1.3.1.4; 2015-08-20: Unit Test
|  | 1.3.1.5 | Get | Aislinn Jewel Caparoso |  |  |  | NA | Medium | NOT DONE | 2015-08-07: 1.3.1.5; 2015-08-12: Unit Test
| 1.3.2 | Event-Controller
|  | 1.3.2.1 | Create | James Suson |  |  |  | NA | High | NOT DONE | 2015-07-30: 1.3.2.1; 2015-08-05: Unit Test
|  | 1.3.2.2 | Update | Charlie Ahl Arreglo |  |  |  | NA | High | NOT DONE | 2015-07-30: 1.3.2.2; 2015-08-05: Unit Test
|  | 1.3.2.3 | Delete | Noville Lao Villanueva |  |  |  | NA | High | NOT DONE | 2015-07-30: 1.3.2.3; 2015-08-05: Unit Test
|  | 1.3.2.4 | Read | Louie Romares |  |  |  | NA | High | NOT DONE | 2015-07-30: 1.3.2.4; 2015-08-05: Unit Test
1.4 Create Services
| 1.4.1 | User Service |  | Noville Lao Villanueva |  |  |  | NA | Medium | NOT DONE | 2015-08-14: 1.4.1; 2015-08-20: Unit Test
| 1.4.2 | Event Service |  | Ted Ian Osias |  |  |  | NA | High | NOT DONE | 2015-07-30: 1.4.2; 2015-08-05: Unit Test
| 1.4.3 | UserInfo Service |  | James Suson |  |  |  | NA | Low | NOT DONE | 2015-08-24: 1.4.3; 2015-08-27: Unit Test
Front-End(2.0)
2.1 Views
| 2.1.1 | Login |  | Louie Romares |  |  |  | NA | Low | NOT DONE | 2015-07-08: 2.1.1
| 2.1.2 | Mainpage
| 2.1.2.1 |  | Carousel | Louie Romares |  |  |  | NA | Low | NOT DONE
| 2.1.2.2 |  | GridView | Charlie Ahl Arreglo | 2015-07-03 | 2015-07-06 | 2015-07-03 | 2015-07-06 | High | DONE | 2015-07-03: 2.1.2.2; 2015-07-08: 2.1.2.1
| 2.1.3 | NavigationPane |  | Ted Ian Osias | 2015-07-03 | 2015-07-06 | 2015-07-03 | 2015-07-06 | High | DONE | 2015-07-03: 2.1.3
| 2.1.4 | Create-Event |  | Charlie Ahl Arreglo |  |  |  | NA | Medium | NOT DONE | 2015-07-08: 2.1.4
| 2.1.5 | EditEvent |  | Aislinn Jewel Caparoso |  |  |  | NA | Medium | NOT DONE | 2015-07-08: 2.1.5
| 2.1.6 | ViewEvent |  | Aislinn Jewel Caparoso | 2015-07-03 | 2015-07-06 | 2015-07-03 | 2015-07-06 | High | DONE | 2015-07-03: 2.1.6
| 2.1.7 | SearchEvent |  | Louie Romares | 2015-07-03 | 2015-07-06 | 2015-07-03 | NA | High | NOT DONE | 2015-07-03: 2.1.7
| 2.1.8 | Settings |  | James Suson | 2015-07-03 | 2015-07-06 | 2015-07-03 | NA | Medium | NOT DONE | 2015-07-03: 2.1.8
| 2.1.9 | Profile |  | Noville Lao Villanueva | 2015-07-03 | 2015-07-06 | 2015-07-03 | 2015-07-09 | Medium | DONE | 2015-07-03: 2.1.9
| 2.1.10 | Error |  | Ted Ian Osias |  |  |  | NA | High | NOT DONE | 2015-07-08: 2.1.10
2.2 View Controllers
| 2.2.1 | Login |  | Louie Romares |  |  |  | NA | Low | NOT DONE | 2015-07-15: 2.2.1
| 2.2.2 | Mainpage |  | Charlie Ahl Arreglo |  |  |  | NA | High | NOT DONE | 2015-07-15: 2.2.2
| 2.2.3 | NavigationPane |  | Ted Ian Osias |  |  |  | NA | Medium | NOT DONE | 2015-07-15: 2.2.3
| 2.2.4 | Event |  | Aislinn Jewel Caparoso |  |  |  | NA | High | NOT DONE | 2015-07-15: 2.2.4
| 2.2.5 | Settings |  | James Suson |  |  |  | NA | Medium | NOT DONE | 2015-07-15: 2.2.5
| 2.2.6 | Profile |  | Noville Lao Villanueva |  |  |  | NA | Medium | NOT DONE | 2015-07-15: 2.2.6
Testing(3.0)
| 3.1 Integration Test | [9 empty] | 2015-08-31: INTEGRATION TEST
| 3.2 Regressioin Test | [9 empty] | 2015-09-08: REGRESSION TEST
| 3.3 System Test | [9 empty] | 2015-09-15: SYSTEM TEST
Review
| 4.1 Review 1 | [9 empty] | 2015-09-04: REVIEW CODE
| 4.2 Review 2 | [9 empty] | 2015-09-21: REVIEW, ADD-ONS, AND DEFENSE PRACTICE

## Sheet1
2015-07-03 | 2015-07-06 | 2015-07-07 | 2015-07-08 | 2015-07-09 | 2015-07-10 | 2015-07-13 | 2015-07-14 | 2015-07-15 | 2015-07-16 | 2015-07-17
2.1.2.2 |  |  | 2.1.1 |  |  |  |  | 2.2.1
2.1.3 |  |  | 2.1.2.1 |  |  |  |  | 2.2.2
2.1.6 |  |  | 2.1.10 |  |  |  |  | 2.2.3
2.1.7 |  |  | 2.1.4 |  |  |  |  | 2.2.4
2.1.8 |  |  | 2.1.5 |  |  |  |  | 2.2.5
2.1.9 | [7 empty] | 2.2.6
2015-07-20 | 2015-07-21 | 2015-07-22 | 2015-07-23 | 2015-07-24 | 2015-07-27 | 2015-07-28 | 2015-07-29 | 2015-07-30 | 2015-07-31 | 2015-08-03
2.2.1 |  |  | 1.1.1 | [5 empty] | Unit Test
2.2.2 |  |  | 1.1.2 | [5 empty] | Unit Test
2.2.3 |  |  | 1.2.3.1 | [5 empty] | Unit Test
2.2.4 |  |  | 1.2.3.2 | [5 empty] | Unit Test
2.2.5 |  |  | 1.2.3.3 | [5 empty] | Unit Test
2.2.6 |  |  | 1.2.3.4 | [5 empty] | Unit Test
2015-08-04 | 2015-08-05 | 2015-08-06 | 2015-08-07 | 2015-08-10 | 2015-08-11 | 2015-08-12 | 2015-08-13 | 2015-08-14 | 2015-08-17 | 2015-08-18
1.3.2.1 |  |  |  | Unit Test |  | 1.2.1.2 |  |  | Unit Test
1.3.2.2 |  |  |  | Unit Test |  | 1.2.1.3 |  |  | Unit Test
1.3.2.3 |  |  |  | Unit Test |  | 1.2.1.4 |  |  | Unit Test
1.3.2.4 |  |  |  | Unit Test |  | 1.3.1.5 |  |  | Unit Test
1.4.2 |  |  |  | Unit Test |  | 1.3.1.1 |  |  | Unit Test
1.2.1.1 |  |  |  | Unit Test |  | 1.2.2.1 |  |  | Unit Test
2015-08-19 | 2015-08-20 | 2015-08-21 | 2015-08-24 | 2015-08-25 | 2015-08-26 | 2015-08-27 | 2015-08-28 | 2015-08-31 | 2015-09-01 | 2015-09-02
1.3.1.2 |  |  |  | Unit Test |  | 1.2.2.4 |  |  | Unit Test
1.3.1.3 |  |  |  | Unit Test |  | 1.4.3 |  |  | Unit Test
1.3.1.4 |  |  |  | Unit Test |  | Integration( Noville, Ian, Aislinn, Charlie)
1,2.2.2 |  |  |  | Unit Test
1.2.2.3 |  |  |  | Unit Test
1.4.1 |  |  |  | Unit Test
2015-09-03 | 2015-09-04 | 2015-09-07 | 2015-09-08 | 2015-09-09 | 2015-09-10 | 2015-09-11 | 2015-09-14 | 2015-09-15 | 2015-09-16 | 2015-09-17
INTEGRATION TEST |  |  |  | REVIEW CODE |  | REGRESSION TEST
2015-09-18 | 2015-09-21 | 2015-09-22 | 2015-09-23 | 2015-09-24 | 2015-09-25 | 2015-09-28 | 2015-09-29 | 2015-09-30
SYSTEM TEST |  |  |  | REVIEW, ADD-ONS, AND DEFENSE PRACTICE